## Calendar
Governance formation calendar - CIO - example 18 month timeline | Owner | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | KEY
PHASES |  | 1: INITIAL SET UP; 7: CHARITY FORMATION; 15: POST REGISTRATION SET-UP | RECURRING
1: Foundational principle work | [19 empty] | ALLOCATED TIME
Basic terms of reference for group across all key areas | [19 empty] | STALLED | bar: 1
Organisation structure review | [19 empty] | COMPLETE | bar: 1 to 2
Organisational Charity Commission registration application + processing | bar: 8 to 14
2: Organisation Purpose
Objects drafting/review | bar: 6 to 7
Charitable purpose assessment | bar: 6 to 7
Public benefit assessment of proposed charitable activities | bar: 6 to 7
Strategy setting/theory of change | bar: 1 to 6
3: Leadership
Core Volunteer recruitment (assuming some initial group members) | SLT | bar: 1 to 6
Trustee Recruitment and Appointment Process | bar: 3 to 6
SLT/Existing Leadership Initial Skills Audit | bar: 2
Trustee Eligibility Declarations/Checks | bar: 6
Trustee Induction | bar: 7
Member list (keep updated) or trustee changes notification to commission | bar: 15
4: Ethics and culture
Code of Conduct drafting | bar: 1
Raising a concern and complaints policy drafting and implementation | bar: 4 to 5
Conflict of interest policy + register drafting and implementation | bar: 4 to 5
5: Decision Making
Monthly SLT group meetings
Volunteer/Staff roles and responsibilities documentation | bar: 1
Scheme of delegation drafting | bar: 6
Safeguarding work needs assessment/safeguarding policy drafting | bar: 4 to 5
Quarterly Board Meetings inc. policy approvals | BOARD | 7: APPROVE APPLICATION; 11: UPDATE; 15: 1; 18: 2
Committees Terms Of Reference drafting- add as appropriate | bar: 13 to 14
Quarterly [X] Committee meeting | bar: 17
6: Managing resources and risk
Risk register drafting | bar: 4 to 5
Risk management policy drafting | bar: 4 to 5
Insurance | bar: 15 to 16
Financial controls inc. reserves position drafting | bar: 4 to 5
Basic privacy policy drafting | bar: 14 to 15
HMRC/gift aid registration | bar: 15
Data protection registration (as necessary) | bar: 15
Charity bank account opening | bar: 15 to 17
7: EDI
Diversity audit | bar: 18
EDI policy drafting + implementation | bar: 6 to 7
8:Board effectiveness
Volunteer skills mapping inc. for trustee board formation | bar: 1 to 2
Publication of policies/constitution/governance documents on website | bar: 8 to 18
Charity Governance Code Internal Audit | bar: 18